****

**2010-2011 Planning Schedule**

* **October 21, 2010 – Kick Off Meeting**
* **December 1 - 3, 2010 – 3 days**
	+ *Strategy Session #1* – Core Team & Steering Committee
	+ *College-wide Forum #1* – Wednesday, Dec 1, 2010 **(TBD)**
	+ *Interviews & Visitations* – Learning Centers, ISD, Contract Education, Distance Learning & Department Chair Sessions
	+ *Strategy Sessions* – External Stakeholders & Students
* **February 4, 2011**
	+ *Strategy Session #2* – **All College Workshop** at Le-Jao Center
* **March 16 - 17, 2011 – 2 days**
	+ *Strategy Session #3* – Core Team & Steering Committee
	+ *College-wide Forum #2* – Wednesday, March 16, 2010 **(TBD)**
* **Week of April 11, 2011**
	+ Draft *Education Master Plan* report ready for review
	+ Available for feedback from the Coastline College
* **Week of May 2, 2011**
	+ *Education Master Plan* report finalized

*\*\*Days and times will also be available on the Educational Master Plan Website\*\**

<http://www.coastline.edu/masterplan>